## Key Account
List of Jobs Assigned to Al Tawainah
| KEY ACCOUNT : Eng. Mohammed Al Shehri | [5 empty] | Updated: 20-12-2011
Sl | Exch. | Site Name | Civil Job No | Civil Status | Civil Remarks | Fiber Job No. | Fiber Contractor | Fiber Remarks | Fiber Remarks | Plan Receive Date
LIST OF CIVIL + FIBER JOB - AL TAWAINAH
1 | NSHS | Municipality of Riyadh (NSHS) | 1111003453 | Completed |  | 1111003454 | Al Taawniah | In Progress | Will complete within 4 days | 23/10/2011
2 | NWRY | Municipaltiy of Riyadh (NWRY) | 1111003466 | Completed |  | 1111003465 | Al Taawniah | In Progress - 90% | 90% Waiting for Spliter | 2011-01-11
3 | TWIQ | Ministry of Interior | 1111001029 | Completed |  | 1111001030 | Al Taawniah | In Progress - 90% | NEED DOWN TIME | OLD
4 | MATH | Prince Naif Palace | 1111001087 | In Progress | Received Permission from Development of Riyadh Dept. on 20/12/2011- Planning to Start on 22/12/2011 | 1111001088 | Al Taawniah | Not Started | Waiting for Civil Job | 21/04/2011
5 | KALJ | El Seif Bldg | 1111002246 | In Progress | Job In Progress - Expected to Completed by the End of next Week | 1111002248 | Al Taawniah | Not Started | Waiting for Civil Job | 2011-01-10
6 | MANF | Municipaltiy of Riyadh (Batha) | 1111003527 | Not Started | Permit Ready – Unable to Start due to More Utilities | 1111003528 | Al Taawniah | Not Started | Waiting for Civil Job | 29/10/2011
7 | ERJA | Saudi Fransi Bank | 1111002938 | Not Started | Waiting for MOT / Traffic Permit | 1111002939 | Al Taawniah | Not Started | Waiting for Civil Job | 2011-12-09
8 | AMAL |  | 1011002862 | Not Started | MOT - NOT AGREE FOR THIS ROUTE | 1011002863 | Al Taawniah | Not Started | Waiting for Civil Job | OLD
9 | KHRR- ESUL | Land Forces (King Abdullah Hay) | 1111003873 | Not Started | Permit In Progress | 1111003571 | Al Taawniah | Not Started | Waiting for Civil Job | 26/10/2011
10 | SHOB | Riyadh Bank | 1111003632 | Not Started | Permit In Progress | 1111003633 | Al Taawniah | Not Started | Waiting for Civil Job | 13/12/2011
11 | NSHS | Riyadh Bank-SHBRRDOA | 1111003778 | Not Started | Permit In Progress | 1111003810 | Al Taawniah | Not Started | Waiting for Civil Job | 14/12/2011
12 | MATH | MOI HQ Security Affairs-Diplomatic QR | 1111002561 | Not Started | Need to CANCEL | 1111002669 | Al Taawniah | Not Started | Waiting for Civil Job | 2011-05-10
LIST OF ONLY CIVIL JOBS - AL TAWAINAH
1 | AULA | Al Ajou Group - MOI Anti Drug | 1111002705 | Not Started | Waiting for MOT / Traffic Permit |  |  |  |  | 2011-01-10
2 | NSHN | Municipaltiy of Riyadh (Mather) | 1111003522 | Not Started | Waiting for MOT / Traffic Permit |  |  |  |  | 29/10/2011
3 | ADLS | MH to MH | 1111003548 | Not Started | Permit In ProgNeed to Change route and issue new plan as it is impossible to work as per the old route. Please ask your PM to discuss with our Project Manager to Find some solution ress |  |  |  |  | 2011-01-11
4 | NWRY | Municipaltiy of Riyadh -Graveyard (NWRY | 1111002987 | Not Started | Permit In Progress |  |  |  |  | 16/10/2011
5 | AMAL | Cable replacement | 1111001496 | Not Started | Permit Ready – Unable to Start due to More Utilities |  |  |  |  | 15/08/2011
6 | NDAH | Riyadh Bank | 1111003563 | Not Started | Permit In Progress |  |  |  |  | 27/11/2011
7 | KHRR | Khuris Road | 1111003624 | Not Started | Need to Change route and issue new plan as it is impossible to work as per the old route. Please ask your PM to discuss with our Project Manager to Find some solution |  |  |  |  | 2011-03-12
LIST OF ONLY FIBER JOBS - AL TAWAINAH
1 | NWRC | Municipality of Riyadh (AD DIRAH) |  |  |  | 1111003400 | Al Taawniah | In Progress - 90% | Waiting for Spliter | 23/10/2011
2 | ERJA | Municipaltiy of Riyadh (ERJA) |  |  |  | 1111003452 | Al Taawniah | In Progress - 90% | Waiting for Spliter | 29/10/2011
3 | KALJ | El Seif Contracting Co |  |  |  | 1111002281 | Al Taawniah | In Progress - 90% | Waiting for Spliter | 2011-05-10
4 | NWRC | GSM- |  |  |  | 1111001100 | Al Taawniah | In Progress | One Side we need access | 31/07/2011
5 | NWRC | Al Rajhi Bank - MRGBRDAF |  |  |  | 1111002610 | Al Taawniah | In Progress | No Existing ODB in the Bank | 18/09/2011
6 | ALKR | Junction-ALKR-NWSN |  |  |  | 1111002423 | Al Taawniah | In Progress - 80% | 80% completed – Need Permission in ALKR exchange | 2011-02-10
7 | ERJA-SHIM | Municipality of Riyadh Compound - Shimeisy Area |  |  |  | 1111002968 | Al Taawniah | In Progress | Will complete within 4 days | 13/12/2011
8 | ALSH | Riyadh Bank - SHFAFDOA |  |  |  | 1111003651 | Al Taawniah | In Progress | Will complete within 4 days | 14/12/2011
9 | NWRY | Riyadh Bank |  |  |  | 1111003727 | Al Taawniah | In Progress | Will complete within 4 days | 14/12/2011
10 | KALJ | M.K. Lighting |  |  |  | 1111002252 | Al Taawniah | Not Started | HOLD - Road under construction | 2011-01-10
11 | MURR | MINISTRY OF INFORMATION |  |  |  | 1111002519 | Al Taawniah | Not Started | NEED PERMISSION TO PULLING ALL AREA COVERED BY MILITRY | 15/08/2011
12 | ESUL | STC compound |  |  |  | 1111002534 | Al Taawniah | Not Started | As per the Bldg. Manager during our survey informed his request was old and need to speak to the concern Project Manager of Key Account | 2011-02-10
13 | KKIA | King Khalid Terminal 2 MOI |  |  |  | 1111003085 | Al Taawniah | Not Started | As Discussed with Mr. Abdullah Al Harbi - Will transfer this job to Al Aksab Compnay as they have the permission in this area | 18/09/2011
14 | AULA | King Fahad Library |  |  |  | 1111002857 | Al Taawniah | Not Started | Need Civil - 172mts | 18/07/2011
15 | ESUL | Riyadh Bank - MSEFRDOA |  |  |  | 1111003702 | Al Taawniah | Not Started | Need Civil - 50 mts | 14/12/2011
16 | NSHS | Riyadh Bank |  |  |  | 1111003600 | Al Taawniah | Not Started | Need Civil - 50 mts | 14/12/2011
17 | NWRY | Riyadh Bank - NDMWRDOA |  |  |  | 1111003604 | Al Taawniah | Not Started | Need Civil - 130 mts | 14/12/2011
18 | MATH/ NSHN | Municipality of Riyadh- Ash Sharafiyah |  |  |  | 1111003532 | Al Taawniah | Not Started | Survey Stage | 22/11/2011
19 | ESUL | Riyadh Bank - SAUD Center-Mohamadayh |  |  |  | 1111003629 | Al Taawniah | Not Started | Survey Stage | 27/11/2011
20 | AULA | Riyadh Bank |  |  |  | 1111003706 | Al Taawniah | Not Started | Survey Stage | 14/12/2011
21 | MATH | Saudi Fransi Bank |  |  |  | 1111003753 | Al Taawniah | Not Started | Survey Stage | 14/12/2011
LIST OF JOBS COMPLETED - AL TAWAINAH
1 | AULA | Legent Tower-Fransi Bank | 1111003257 | Completed |  | 1111003248 | Al Taawniah | Completed |  | 2011-12-10
2 | AMAL | Marriot Tower | 1111002049 | Completed |  | 1111001992 | Al Taawniah | Completed
3 | AULA | Prince Naif Mathaar Palace | 1111001890 | Completed |  | 1111001891 | Al Taawniah | Completed
4 | SHOB | Riyadh Municipality | 1111002972 | Completed |  | 1111002973 | Al Taawniah | Completed
5 | KHRR | Ministry of Education | 1011003215 | Completed |  | 1011003216 | Al Taawniah | Completed
6 | AMAL | GOSI BLDG. | 1111002347 | Completed |  | 1111002360 | Al Taawniah | Completed
7 | NSHN | Prince Mohd Bin Saud Bin Khalid Palace | 1011003217 | Completed |  | 1011002783 | Al Taawniah | Completed
8 | NDEM | GID | 1111001069 | Completed |  | 1111001112 | Al Taawniah | Completed
3 | NDAH | National Water | 1111002960 | Completed |  | 1111002961 | Al Taawniah | Completed |  | 2011-12-09
9 | KALJ | MOI-Anti Drug | 1111001466 | Completed |  | NO | NO | NO
10 | ESUL | Blgs. 33 | NO | NO |  | 1111003279 | Al Taawniah | Completed |  | 2011-05-10
11 | NAFL | National Commission Againts Corp. | NO | NO |  | 1111002899 | Al Taawniah | Completed
12 | MURR | MOI-BOURDER GUARD | NO | NO |  | 1111002274 | Al Taawniah | Completed
13 | ESUL | MSAN 721-395 | NO | NO |  | 1111002608 | Al Taawniah | Completed
14 | MATH | MOI COMMNNICATION | NO | NO |  | 1111002846 | Al Taawniah | Completed
LIST OF JOBS COMPLETED BY ANOTHER COMPANY:
1 | NDAH | Ministry of Education | NO | NO |  | 1011002662 | Al Taawniah | Not Started | Completed by another contractor as per Mr. Khaja
2 | AULA | ANB | NO | NO |  | 1111002069 | Al Taawniah | Not Started | Completed by another contractor
3 | AULA | TAWREEN TOWER | NO | NO |  | 1111002282 | Al Taawniah | Not Started | Completed by another contractor